## Sheet1
GEAR SELLING WEB
PRODUCT BACKLOG
Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Start date | End date | Actual end date | Status | Note
Login | Front-end design login page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Login | Front-end design register page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-14 | 2023-02-14 | 2023-02-14 | Done
Login | Front-end design forget password page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-14 | Done
Login | Front-end design profile page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-15 | Done
Login | Front-end design reset password page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Done
Login | Login | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Done
Login | Logout | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Done
Home | Load comment of customer | Medium | Iteration 3 | CE160451 | Le Quoc Thang | Iteration 3 | 2023-03-03 | 2023-03-04 | 2023-03-04 | Done
Home | Comment Product | Medium | Iteration 3 | CE160451 | Le Quoc Thang | Iteration 3 | 2023-03-03 | 2023-03-04 | 2023-03-04 | Done
Home | Front-end Design Sale product page | Simple | Iteration 1 | CE160451 | Le Quoc Thang | Iteration 1 | 2023-02-22 | 2023-02-22 | 2023-02-22 | Done
Home | Front-end design home page | Medium | Iteration 1 | CE161037 | Ho Nhat Minh | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Home | Front-end design order confirmation page | Simple | Iteration 1 | CE161037 | Ho Nhat Minh | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Home | Front-end design order history page | Simple | Iteration 1 | CE161037 | Ho Nhat Minh | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Home | Front-end design all list product page | Simple | Iteration 1 | CE161037 | Ho Nhat Minh | Iteration 1 | 2023-02-14 | 2023-02-14 | 2023-02-14 | Done
Login | Register | Simple | Iteration 2 | CE161037 | Ho Nhat Minh | Iteration 1 | 2023-02-21 | 2023-02-22 | 2023-02-16 | Done
Home | View profile | Simple | Iteration 2 | CE161037 | Ho Nhat Minh | Iteration 2 | 2023-02-21 | 2023-02-21 | 2023-02-21 | Done
Home | Edit Profile | Simple | Iteration 2 | CE161037 | Ho Nhat Minh | Iteration 3 | 2023-02-23 | 2023-02-24 | 2023-02-27 | Done
Login | Forget password | Medium | Iteration 3 | CE161037 | Ho Nhat Minh | Iteration 2 | 2023-02-27 | 2023-02-27 | 2023-02-20 | Done
Login | Reset password | Simple | Iteration 3 | CE161037 | Ho Nhat Minh | Iteration 2 | 2023-02-28 | 2023-02-28 | 2023-02-28 | Done
Sale management | Front-end design view all sale page | Simple | Iteration 1 | CE161020 | Nguyen Thanh Dat | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Done
Sale management | Front-end design add sale page | Simple | Iteration 1 | CE161020 | Nguyen Thanh Dat | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Done
Sale management | Front-end design update sale page | Simple | Iteration 1 | CE161020 | Nguyen Thanh Dat | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-18 | Done
Sale management | Load all sale | Simple | Iteration 2 | CE161020 | Nguyen Thanh Dat | Iteration 2 | 2023-02-20 | 2023-02-20 | 2023-02-20 | Done
Sale management | Search sale | Simple | Iteration 2 | CE161020 | Nguyen Thanh Dat | Iteration 2 | 2023-02-20 | 2023-02-20 | 2023-02-20 | Done
Sale management | Add sale | Simple | Iteration 2 | CE161020 | Nguyen Thanh Dat | Iteration 2 | 2023-02-21 | 2023-02-21 | 2023-02-21 | Done
Sale management | Update sale | Simple | Iteration 2 | CE161020 | Nguyen Thanh Dat | Iteration 2 | 2023-02-22 | 2023-02-22 | 2023-02-22 | Done
Sale management | Delete sale | Simple | Iteration 2 | CE161020 | Nguyen Thanh Dat | Iteration 2 | 2023-02-22 | 2023-02-22 | 2023-02-22 | Done
Contact Managent | Load contact list | Simple | Iteration 3 | CE161020 | Nguyen Thanh Dat | Iteration 3 | 2023-03-08 | 2023-03-08 | 2023-03-10 | Done | Late
Contact Managent | Design front end contact list | Simple | Iteration 3 | CE161020 | Nguyen Thanh Dat | Iteration 3 | 2023-03-08 | 2023-03-08 | 2023-03-10 | Done | Late
Warehouse management | Front-end design view all consignment page | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Done
Warehouse management | Front-end design add consignment page | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-17 | Done
Warehouse management | Front-end design update consignment page | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-17 | Done
Warehouse management | Load all consignment | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-19 | Done
Warehouse management | Search consignment | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-19 | Done
Warehouse management | Add consignment | Simple | Iteration 1 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-19 | Done
Warehouse management | Update consignment | Simple | Iteration 2 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-20 | 2023-02-20 | 2023-02-19 | Done
Warehouse management | Delete consignment | Simple | Iteration 2 | CE171144 | Le Truc Nhi | Iteration 1 | 2023-02-20 | 2023-02-20 | 2023-02-19 | Done
Warehouse management | Front-end design product statistic page | Simple | Iteration 2 | CE171144 | Le Truc Nhi | Iteration 2 | 2023-02-21 | 2023-02-23 | 2023-02-23 | Done
Warehouse management | Product statistic | Complex | Iteration 2 | CE171144 | Le Truc Nhi | Iteration 3 | 2023-02-23 | 2023-02-25 | 2023-03-02 | Done | Late
Revenue statistic | Front-end design Revenue statistic page | Simple | Iteration 3 | CE171144 | Le Truc Nhi | Iteration 3 | 2023-02-26 | 2023-02-28 | 2023-03-02 | Done | Late
Revenue statistic | Revenue statistic | Complex | Iteration 3 | CE171144 | Le Truc Nhi | Iteration 3 | 2023-03-01 | 2023-03-03 | 2023-03-02 | Done
Admin Home | Front-end design Admin home page | Simple | Iteration 1 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-17 | Done
Account management | Front-end design Add account page | Simple | Iteration 1 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-17 | Done
Account management | Front-end design Edit account page | Simple | Iteration 1 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-17 | Done
Account management | Front-end design All account page | Simple | Iteration 1 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-19 | 2023-02-19 | 2023-02-17 | Done
Account management | Load all account | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-20 | 2023-02-20 | 2023-02-18 | Done
Account management | Add Account | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-20 | 2023-02-20 | 2023-02-19 | Done
Account management | Edit account | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-21 | 2023-02-21 | 2023-02-18 | Done
Account management | Delete account | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 1 | 2023-02-21 | 2023-02-21 | 2023-02-18 | Done
Order management | Front-end design All order page | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 2 | 2023-02-22 | 2023-02-22 | 20/0/2023 | Done
Order management | Front-end design Order status page | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 2 | 2023-02-22 | 2023-02-22 | 20/0/2023 | Done
Order management | Load view All Order | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 2 | 2023-02-23 | 2023-02-23 | 20/0/2023 | Done
Order management | Confirm Return Order | Simple | Iteration 3 | CE171446 | Do Huynh Anh Vu | Iteration 3 | 2023-03-02 | 2023-03-02 | 2023-03-02 | Done
Order management | Confirm Order | Medium | Iteration 3 | CE171446 | Do Huynh Anh Vu | Iteration 3 | 2023-03-03 | 2023-03-03 | 2023-03-03 | Done
Order management | Change order | Simple | Iteration 2 | CE171446 | Do Huynh Anh Vu | Iteration 2 | 2023-02-23 | 2023-02-24 | 2023-02-21 | Done
Home | Front end design Cart page | Simple | Iteration 1 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Order | Front end design Order return | Simple | Iteration 1 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Order | Front end design Order detail | Simple | Iteration 1 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-13 | 2023-02-13 | 2023-02-13 | Done
Home | Front end design Product detail page | Simple | Iteration 1 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Done
Home | Load signature product | Simple | Iteration 1 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-17 | 2023-02-17 | 2023-02-17 | Done
Home | Load all list Product | Simple | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 1 | 2023-02-18 | 2023-02-18 | 2023-02-18 | Done
Home | Product Detail | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-19 | 2023-02-19 | 2023-02-19 | Done
Home | Search product | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-20 | 2023-02-21 | 2023-02-21 | Done
Home | Load category | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-20 | 2023-02-21 | 2023-02-21 | Done
Home | Load product by category | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-20 | 2023-02-21 | 2023-02-21 | Done
Home | Sort product by price | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-20 | 2023-02-21 | 2023-02-21 | Done
Order | Add product to cart | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Done
Home | Load product in cart | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Done
Home | Adjust product price according to discount | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Done
Home | Load product sale | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Done
Order | Product billing | Medium | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-21 | 2023-02-22 | 2023-02-22 | Done
Order | Payment confirmation | Complex | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-23 | 2023-02-23 | 2023-02-23 | Done
Order | Order History | Simple | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-23 | 2023-02-24 | 2023-02-24 | Done
Home | Load list Sale Product | Simple | Iteration 2 | CE161036 | Tran Ba Nam | Iteration 2 | 2023-02-24 | 2023-02-24 | 2023-02-25 | Done
Contact | Front end Design contact page | Simple | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-02-27 | 2023-02-27 | 2023-03-03 | Done
Contact | Contact mail | Medium | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-02-28 | 2023-02-28 | 2023-03-03 | Done
Order | Order return | Medium | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-03-12 | 2023-03-12 | 2023-03-12 | Done
Order | Order confirmation | Simple | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-03-12 | 2023-03-12 | 2023-03-12 | Done
Order | Delete Item Cart | Medium | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-03-12 | 2023-03-12 | 2023-03-12 | Done
Order | Order detail | Medium | Iteration 3 | CE161036 | Tran Ba Nam | Iteration 3 | 2023-03-12 | 2023-03-12 | 2023-03-12 | Done